## Sheet1
TEMPLATE UPLOAD MASTER SITE PROGRESS | [8 empty] | IC_000010 | TSS_000030 | IC_000030 | IC_000040 | IC_000070 | IC_000080 | IC_000090 | IC_000100 | IC_000115 | RFOA | RFOA | RFOA | Blocking Issues | Issue Owner | ACPT_000020
POIN v2 | 2016-12-01 | NOKIA | [6 empty] | Ready For Installation | Technical Site Survey - RBS | Material Delivered to Site | TI Installation Finish | G900 MHz ON AIR | 1800 MHz ON AIR | 2100 MHz ON AIR | U900 Mhz ON AIR | LTE 1800 MHz - 10 MHz - ON AIR | Full OA | Full OA | Full OA | Installation & Commissioning Issues | Issue Owner | RAN Acceptance Visit
check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | check master site info | date | date | date | date | date | date | date | date | date | date | date | free text | free text | free text | date | free text | free text | free text | please ignore blank | please ignore blank | please ignore blank | please ignore blank
NOKIA | NOKIA | SITE_ID | SITE_NAME | PROGRAM | WBS_STATUS | REGION | PROJECT | NOKIA | IC_000010_AF | TSS_000030_AF | IC_000030_AF | IC_000040_AF | IC_000070_AF | IC_000080_AF | IC_000090_AF | IC_000100_AF | IC_000115_AF | Baseline Finish | Actual Finish | Actual Week | IC_ISSUES | IC_OWNER | ACPT_000020_AF | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA | NOKIA
ID | BOQ No | Site ID | Site Name | SOW Category | Site Status | Region Code | Phase Name | NE Name | RFI | TSS | MOS | Installed | G900 | G1800 | U2100 | U900 | L1800 | ON AIR Baseline | ON AIR Date | ON AIR Week | IC_ISSUES | IC_OWNER | ATP Date | ATP Method | Partner NI | Indosat PIC | Update By | Update Date | Upload ID | Status
100001 | LTE15MHZ0001 | 08BKT003 | L_AUR_KUNING2 | Activation LTE 15 Mhz + Modernization RF Modul |  |  | LTE 15 MHz |  | 2017-01-19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 42757 |  |  |  | 42764 |  |  |  | admin | 2017-01-21 23:07:55 | 2 | 1
100001 | LTE15MHZ0001 | 08BKT003 | L_AUR_KUNING2 | Activation LTE 15 Mhz + Modernization RF Modul |  |  | LTE 15 MHz |  | 2017-01-19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 42757 |  |  |  | 42764 |  |  |  | admin | 2017-01-21 23:07:55 | 3 | 1
100002 | LTE15MHZ0002 | 08PAD002 | ANDURING | upgrade TRX (EGSM) + Replace Filter |  |  | LTE 15 MHz |  | 2017-01-19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 42759 |  |  |  | 42763 |  |  |  | admin | 2017-01-21 22:37:11 | 2 | 1
100002 | LTE15MHZ0002 | 08PAD002 | ANDURING | upgrade TRX (EGSM) + Replace Filter |  |  | LTE 15 MHz |  | 2017-01-19 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 42759 |  |  |  | 42763 |  |  |  | admin | 2017-01-21 22:37:11 | 3 | 1
100003 | LTE15MHZ0003 | 08PAD002 | ANDURING | Retune Filter Only | Active | NS | LTE 15 MHz | BTS | 2017-01-20 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE |  |  |  | admin | 2017-01-18 18:09:10 | 2 | 1
100003 | LTE15MHZ0003 | 08PAD002 | ANDURING | Retune Filter Only | Active | NS | LTE 15 MHz | BTS | 2017-01-20 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE |  |  |  | admin | 2017-01-18 18:09:10 | 3 | 1
100004 | LTE15MHZ0004 | 08PAD007 | IL_LUBUK_BEGALUNG | Activation LTE 15 Mhz + Modernization RF Modul | Active |  | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100005 | LTE15MHZ0005 | 08PAD012 | IL_SITEBA | Activation LTE 15 Mhz | Active | NS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100006 | LTE15MHZ0006 | 08PAD013 | IL_TELUK_BAYUR | Activation LTE 15 Mhz |  |  | LTE 15 MHz |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100007 | LTE15MHZ0007 | 08PAD020 | IL_PAMPANGAN_PDG | Activation LTE 15 Mhz + Modernization RF Modul |  |  | LTE 15 MHz |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100008 | LTE15MHZ0008 | 08PAD022 | L_AIR_TAWAR_XYX | Activation LTE 15 Mhz + Modernization RF Modul |  |  | LTE 15 MHz |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100009 | LTE15MHZ0009 | 08PAD059 | IL_KHATIB_SULAIMAN | Activation LTE 15 Mhz | Active | NS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100010 | LTE15MHZ0010 | 13KLA005 | IL_TANJUNG_SENANG | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100011 | LTE15MHZ0011 | 13KLA007 | IL_UNILA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100012 | LTE15MHZ0012 | 13KLA008 | IL_UNTUNG_SUROPATI | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100013 | LTE15MHZ0013 | 13KLA008 | IL_UNTUNG_SUROPATI | upgrade TRX (EGSM) + Replace Filter | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100014 | LTE15MHZ0014 | 13KLA008 | IL_UNTUNG_SUROPATI | Retune Filter Only | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100015 | LTE15MHZ0015 | 13KLA009 | IL_WAY_HALIM | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100016 | LTE15MHZ0016 | 13KLA019 | IL_KOMPLEK_KOTA_SEPANG | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100017 | LTE15MHZ0017 | 13MER019 | L_KAMPUS UM METRO_CR | Activation LTE 15 Mhz + Modernization RF Modul | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100018 | LTE15MHZ0018 | 13TJK002 | IL_PASAR_KOGA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100019 | LTE15MHZ0019 | 13TJK004 | IL_TAMAN_SISWA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100020 | LTE15MHZ0020 | 13TJK005 | IL_TIRTAYASA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100021 | LTE15MHZ0021 | 13TJK005 | IL_TIRTAYASA | upgrade TRX (EGSM) + Replace Filter | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100022 | LTE15MHZ0022 | 13TJK005 | IL_TIRTAYASA | Retune Filter Only | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100023 | LTE15MHZ0023 | 13TJK006 | IL_UNIV_BANDAR_LAMPUNG | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100024 | LTE15MHZ0024 | 13TJK006 | IL_UNIV_BANDAR_LAMPUNG | upgrade TRX (EGSM) + Replace Filter | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100025 | LTE15MHZ0025 | 13TJK006 | IL_UNIV_BANDAR_LAMPUNG | Retune Filter Only | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100026 | LTE15MHZ0026 | 13TJK007 | IL_VILLA_CITRA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100027 | LTE15MHZ0027 | 13TJK008 | IL_BUKIT_RANDU | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100028 | LTE15MHZ0028 | 13TJK011 | IL_KARTINI_HOTEL | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100029 | LTE15MHZ0029 | 13TJK012 | L_KEMILING | Activation LTE 15 Mhz + Modernization RF Modul | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100030 | LTE15MHZ0030 | 13TJK013 | IL_PAHOMAN | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100031 | LTE15MHZ0031 | 13TJK015 | IL_GAMASERA | Activation LTE 15 Mhz + Modernization RF Modul | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100032 | LTE15MHZ0032 | 13TJK017 | IL_KEDAMAIAN | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100033 | LTE15MHZ0033 | 13TJK023 | IL_DEPNAKER_LPG | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100034 | LTE15MHZ0034 | 13TJK025 | IL_PASAR_CIMENG | Activation LTE 15 Mhz + Modernization RF Modul | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100035 | LTE15MHZ0035 | 13TJK026 | IL_PASAR_BAMBU_KUNING | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100036 | LTE15MHZ0036 | 13TJK036 | IL_SEPANG_JAYA_PL | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100037 | LTE15MHZ0037 | 13TJK038 | L_MAWAR_TB | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100038 | LTE15MHZ0038 | 13TJK039 | IL_INDRAPURI | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100039 | LTE15MHZ0039 | 13TJK040 | L_U_MALAHAYATI_TB_XYX | Activation LTE 15 Mhz + Modernization RF Modul | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100040 | LTE15MHZ0040 | 13TJK051 | IL_IMMANUEL_BARU | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100041 | LTE15MHZ0041 | 13TJK052 | IL_KUPANG_TIGA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100042 | LTE15MHZ0042 | 13TJK059 | PERUM_DAMRI_RF | upgrade TRX (EGSM) + Replace Filter | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100043 | LTE15MHZ0043 | 13TJK059 | PERUM_DAMRI_RF | Retune Filter Only | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100044 | LTE15MHZ0044 | 13TJK062 | IL_URIPSHARJO_RFA | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100045 | LTE15MHZ0045 | 13TJK080 | IL_PRGELORAPERSADA_GH | Activation LTE 15 Mhz | Active | SS | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100046 | LTE15MHZ0046 | 14DMK001 | DEMAK | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100047 | LTE15MHZ0047 | 14DMK006 | MRANGGEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100048 | LTE15MHZ0048 | 14DMK007 | KLIPANG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100049 | LTE15MHZ0049 | 14DMK008 | SAYUNG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100050 | LTE15MHZ0050 | 14DMK009 | PUCANGGADING | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100051 | LTE15MHZ0051 | 14DMK034 | PENGGARON | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100052 | LTE15MHZ0052 | 14DMK038 | DEMAKKOTAXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100053 | LTE15MHZ0053 | 14KLT002 | KLATEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100054 | LTE15MHZ0054 | 14KLT007 | TEGALYOSOKLTN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100055 | LTE15MHZ0055 | 14KLT008 | KLATENBRT | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100056 | LTE15MHZ0056 | 14KLT009 | BARENGLOR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100057 | LTE15MHZ0057 | 14KLT010 | GERGUNUNG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100058 | LTE15MHZ0058 | 14KLT011 | WEDI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100059 | LTE15MHZ0059 | 14KLT043 | STASIONKLTEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100060 | LTE15MHZ0060 | 14KLT072 | JONGGRANGNIT | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100061 | LTE15MHZ0061 | 14KND002 | CEPIRING | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100062 | LTE15MHZ0062 | 14KND004 | KENDAL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100063 | LTE15MHZ0063 | 14KND005 | KALIWUNGU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100064 | LTE15MHZ0064 | 14KND007 | PATEBON | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100065 | LTE15MHZ0065 | 14KND009 | PEGANDON | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100066 | LTE15MHZ0066 | 14KND028 | BRANGSONG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100067 | LTE15MHZ0067 | 14MGL016 | POTROBANGSA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100068 | LTE15MHZ0068 | 14MKD006 | MUNTILAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100069 | LTE15MHZ0069 | 14MKD008 | KEDUNGSARI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100070 | LTE15MHZ0070 | 14MKD009 | MAGELANGUT | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100071 | LTE15MHZ0071 | 14MKD017 | MAGELANGPOS | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100072 | LTE15MHZ0072 | 14MKD069 | PASAR MUNTILAN | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100073 | LTE15MHZ0073 | 14SMG001 | TAMBAKAJI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100074 | LTE15MHZ0074 | 14SMG003 | GOMBEL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100075 | LTE15MHZ0075 | 14SMG004 | MANYARAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100076 | LTE15MHZ0076 | 14SMG005 | TERBOYO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100077 | LTE15MHZ0077 | 14SMG007 | PATRA_HOTEL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100078 | LTE15MHZ0078 | 14SMG009 | CEMARA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100079 | LTE15MHZ0079 | 14SMG010 | TANAHMAS | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100080 | LTE15MHZ0080 | 14SMG011 | TLOGOSARI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100081 | LTE15MHZ0081 | 14SMG015 | TEMBALANG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100082 | LTE15MHZ0082 | 14SMG016 | BUKITKUSUMA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100083 | LTE15MHZ0083 | 14SMG017 | TUGU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100084 | LTE15MHZ0084 | 14SMG018 | NGALIYAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100085 | LTE15MHZ0085 | 14SMG020 | PUDAKPAYUNG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100086 | LTE15MHZ0086 | 14SMG022 | BANGKONG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100087 | LTE15MHZ0087 | 14SMG023 | KYAI_SALEH | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100088 | LTE15MHZ0088 | 14SMG024 | PRANJASMORO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100089 | LTE15MHZ0089 | 14SMG026 | KEDUNGMUNDU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100090 | LTE15MHZ0090 | 14SMG027 | JLBARITO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100091 | LTE15MHZ0091 | 14SMG028 | TLOGOMULYO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100092 | LTE15MHZ0092 | 14SMG029 | BUKITKENCANA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100093 | LTE15MHZ0093 | 14SMG031 | JAGALAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100094 | LTE15MHZ0094 | 14SMG032 | SAMPANGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100095 | LTE15MHZ0095 | 14SMG033 | CANDIASRI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100096 | LTE15MHZ0096 | 14SMG035 | PAPANDAYAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100097 | LTE15MHZ0097 | 14SMG036 | KALIWIRU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100098 | LTE15MHZ0098 | 14SMG039 | KALIPANCUR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100099 | LTE15MHZ0099 | 14SMG041 | TUGUMUDA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100100 | LTE15MHZ0100 | 14SMG042 | MEDOHO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100101 | LTE15MHZ0101 | 14SMG045 | GENUK | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100102 | LTE15MHZ0102 | 14SMG046 | PATIMURA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100103 | LTE15MHZ0103 | 14SMG048 | KALIBANTENG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100104 | LTE15MHZ0104 | 14SMG049 | TAWANG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100105 | LTE15MHZ0105 | 14SMG050 | TANAHPUTIH | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100106 | LTE15MHZ0106 | 14SMG051 | KETILENG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100107 | LTE15MHZ0107 | 14SMG052 | PEDURUNGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100108 | LTE15MHZ0108 | 14SMG053 | BANYUMANIK | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100109 | LTE15MHZ0109 | 14SMG055 | HASANUDDIN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100110 | LTE15MHZ0110 | 14SMG057 | MANGKANG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100111 | LTE15MHZ0111 | 14SMG058 | UNNESSEKARAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100112 | LTE15MHZ0112 | 14SMG059 | KEDUNGPANE | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100113 | LTE15MHZ0113 | 14SMG060 | BANGETAYU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100114 | LTE15MHZ0114 | 14SMG062 | KALICARI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100115 | LTE15MHZ0115 | 14SMG063 | SRONDOL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100116 | LTE15MHZ0116 | 14SMG064 | UNTAG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100117 | LTE15MHZ0117 | 14SMG066 | MULAWARMANKRAMAS | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100118 | LTE15MHZ0118 | 14SMG067 | TMNRDSALEH | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100119 | LTE15MHZ0119 | 14SMG069 | NOVOTELSMG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100120 | LTE15MHZ0120 | 14SMG079 | PRPP | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100121 | LTE15MHZ0121 | 14SMG091 | Tinjomoyo | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100122 | LTE15MHZ0122 | 14SMG096 | JL_MEDOHO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100123 | LTE15MHZ0123 | 14SMG098 | BANARANUNNES | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100124 | LTE15MHZ0124 | 14SMG099 | PDKPYNGSLTN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100125 | LTE15MHZ0125 | 14SMG100 | NGESREPSLTN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100126 | LTE15MHZ0126 | 14SMG105 | PEKUNDEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100127 | LTE15MHZ0127 | 14SMG109 | GISIKDRONO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100128 | LTE15MHZ0128 | 14SMG115 | JLKARTINI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100129 | LTE15MHZ0129 | 14SMG118 | SAWAHBESARPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100130 | LTE15MHZ0130 | 14SMG119 | SENDANGMULYO_PL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100131 | LTE15MHZ0131 | 14SMG121 | GUNUNGSAWO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100132 | LTE15MHZ0132 | 14SMG127 | PURWOYOSO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100133 | LTE15MHZ0133 | 14SMG132 | PELABUHAN_SMG_PL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100134 | LTE15MHZ0134 | 14SMG135 | GEBANGSARIPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100135 | LTE15MHZ0135 | 14SMG136 | BANGETAYU_KLN_PL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100136 | LTE15MHZ0136 | 14SMG137 | LAMPER_TENGAH_IN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100137 | LTE15MHZ0137 | 14SMG141 | BULUSANPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100138 | LTE15MHZ0138 | 14SMG142 | METESEHSMGPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100139 | LTE15MHZ0139 | 14SMG145 | SEKARAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100140 | LTE15MHZ0140 | 14SMG146 | SUKOREJOSMPLXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100141 | LTE15MHZ0141 | 14SMG149 | AKPOL_PL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100142 | LTE15MHZ0142 | 14SMG153 | RSTLOGOREJOXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100143 | LTE15MHZ0143 | 14SMG158 | UDINUS | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100144 | LTE15MHZ0144 | 14SMG160 | DCSTLOGOSRKLN | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100145 | LTE15MHZ0145 | 14SMG162 | CANDI KENCANA | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100146 | LTE15MHZ0146 | 14SMG165 | INDOSATSMG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100147 | LTE15MHZ0147 | 14SMG182 | STEKOMMAJAPAHIT | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100148 | LTE15MHZ0148 | 14SMG186 | TEMBLNGSLPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100149 | LTE15MHZ0149 | 14SMG187 | PDAMKDMUNDU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100150 | LTE15MHZ0150 | 14SMG188 | STEKOMSLWANGI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100151 | LTE15MHZ0151 | 14SMG191 | TANGGULMAS | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100152 | LTE15MHZ0152 | 14SMG192 | MEGAMAS | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100153 | LTE15MHZ0153 | 14SMG194 | PLAMPITANPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100154 | LTE15MHZ0154 | 14STG001 | SALATIGA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100155 | LTE15MHZ0155 | 14STG002 | SALATIGAKOTA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100156 | LTE15MHZ0156 | 14STG003 | SALATIGASLT | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100157 | LTE15MHZ0157 | 14STG004 | TINGKIR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100158 | LTE15MHZ0158 | 14STG018 | SIDOREJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100159 | LTE15MHZ0159 | 14STG019 | SRATEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100160 | LTE15MHZ0160 | 14STG024 | SALATIGAKTTMXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100161 | LTE15MHZ0161 | 14STG025 | TEGALRJSMGITXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100162 | LTE15MHZ0162 | 14TMG005 | PARAKANTMGG | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100163 | LTE15MHZ0163 | 14UNR001 | BAWEN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100164 | LTE15MHZ0164 | 14UNR002 | KALIGANDU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100165 | LTE15MHZ0165 | 14UNR003 | AMBARAWA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100166 | LTE15MHZ0166 | 14UNR004 | BANDUNGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100167 | LTE15MHZ0167 | 14UNR005 | KLEPU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100168 | LTE15MHZ0168 | 14UNR006 | UNGARANCITY | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100169 | LTE15MHZ0169 | 14UNR008 | PRINGAPUSTM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100170 | LTE15MHZ0170 | 14UNR010 | UNGARANPEMDA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100171 | LTE15MHZ0171 | 14UNR015 | BABADAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100172 | LTE15MHZ0172 | 14UNR039 | KALIREJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100173 | LTE15MHZ0173 | 14UNR047 | RANDUGUNTINPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100174 | LTE15MHZ0174 | 14UNR048 | GHANESA | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100175 | LTE15MHZ0175 | 14UNR051 | SEMBIR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100176 | LTE15MHZ0176 | 14UNR072 | AMBARAWA Selatan | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100177 | LTE15MHZ0177 | 15BTL001 | KADIPIRO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100178 | LTE15MHZ0178 | 15BTL004 | IMOGIRI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100179 | LTE15MHZ0179 | 15BTL006 | WONOCATUR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100180 | LTE15MHZ0180 | 15BTL008 | DONGKELAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100181 | LTE15MHZ0181 | 15BTL009 | MANDING | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100182 | LTE15MHZ0182 | 15BTL011 | KASONGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100183 | LTE15MHZ0183 | 15BTL012 | SEWON | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100184 | LTE15MHZ0184 | 15BTL014 | AKAKOM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100185 | LTE15MHZ0185 | 15BTL016 | GUNUNGSEMPU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100186 | LTE15MHZ0186 | 15BTL017 | PLERET | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100187 | LTE15MHZ0187 | 15BTL018 | POTORONO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100188 | LTE15MHZ0188 | 15BTL019 | UMY | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100189 | LTE15MHZ0189 | 15BTL021 | JEC | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100190 | LTE15MHZ0190 | 15BTL022 | TIMBULHARJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100191 | LTE15MHZ0191 | 15BTL026 | PENDOWOHARJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100192 | LTE15MHZ0192 | 15BTL027 | BANTULIM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100193 | LTE15MHZ0193 | 15BTL043 | NGESTIHARJOSM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100194 | LTE15MHZ0194 | 15BTL044 | JAMBIDAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100195 | LTE15MHZ0195 | 15BTL050 | WIROKERTENSM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100196 | LTE15MHZ0196 | 15BTL068 | KRAPYAKYGY | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100197 | LTE15MHZ0197 | 15SMN005 | GODEAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100198 | LTE15MHZ0198 | 15SMN006 | TIMOHO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100199 | LTE15MHZ0199 | 15SMN010 | MLATI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100200 | LTE15MHZ0200 | 15SMN011 | BESI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100201 | LTE15MHZ0201 | 15SMN013 | GEJAYAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100202 | LTE15MHZ0202 | 15SMN014 | TEGALREJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100203 | LTE15MHZ0203 | 15SMN015 | NGAGLIK | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100204 | LTE15MHZ0204 | 15SMN017 | GAMPING | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100205 | LTE15MHZ0205 | 15SMN023 | KARANGWUNI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100206 | LTE15MHZ0206 | 15SMN024 | SAHID | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100207 | LTE15MHZ0207 | 15SMN026 | MRICAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100208 | LTE15MHZ0208 | 15SMN027 | SIDOARUM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100209 | LTE15MHZ0209 | 15SMN028 | NOGOTIRTO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100210 | LTE15MHZ0210 | 15SMN030 | SETURAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100211 | LTE15MHZ0211 | 15SMN032 | JANTI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100212 | LTE15MHZ0212 | 15SMN034 | BANTULAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100213 | LTE15MHZ0213 | 15SMN044 | KENTUNGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100214 | LTE15MHZ0214 | 15SMN061 | PRINGGOLAYAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100215 | LTE15MHZ0215 | 15SMN062 | NANDANPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100216 | LTE15MHZ0216 | 15SMN065 | SINDUHARJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100217 | LTE15MHZ0217 | 15SMN068 | CONCAT | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100218 | LTE15MHZ0218 | 15SMN069 | JAMBUSARISL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100219 | LTE15MHZ0219 | 15SMN078 | DEMANGANBARU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100220 | LTE15MHZ0220 | 15SMN079 | NGABENKULON_PL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100221 | LTE15MHZ0221 | 15SMN080 | JLMAGELANG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100222 | LTE15MHZ0222 | 15SMN081 | RKSAMIRONO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100223 | LTE15MHZ0223 | 15SMN083 | SAGAN | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100224 | LTE15MHZ0224 | 15SMN084 | GANCAHANTBG | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100225 | LTE15MHZ0225 | 15SMN090 | JIH | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100226 | LTE15MHZ0226 | 15SMN093 | GEJAYANSLTNPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100227 | LTE15MHZ0227 | 15SMN095 | MONJALISLTNPL | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100228 | LTE15MHZ0228 | 15YOG001 | NATOUR | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100229 | LTE15MHZ0229 | 15YOG002 | KOTAGEDE | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100230 | LTE15MHZ0230 | 15YOG003 | KUSUMANEGARA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100231 | LTE15MHZ0231 | 15YOG004 | NOVOTELYGY | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100232 | LTE15MHZ0232 | 15YOG005 | PUGERAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100233 | LTE15MHZ0233 | 15YOG006 | WIROBRAJAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100234 | LTE15MHZ0234 | 15YOG009 | GIWANGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100235 | LTE15MHZ0235 | 15YOG010 | UMBULHARJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100236 | LTE15MHZ0236 | 15YOG011 | MATARAM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100237 | LTE15MHZ0237 | 15YOG015 | MUJAMUJU | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100238 | LTE15MHZ0238 | 15YOG016 | COKROAMINOTO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100239 | LTE15MHZ0239 | 15YOG017 | PURBAYAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100240 | LTE15MHZ0240 | 15YOG018 | KRANGGAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100241 | LTE15MHZ0241 | 15YOG019 | BACIRO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100242 | LTE15MHZ0242 | 15YOG020 | LIMAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100243 | LTE15MHZ0243 | 15YOG021 | GONDOSULI | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100244 | LTE15MHZ0244 | 15YOG023 | GONDOMANAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100245 | LTE15MHZ0245 | 15YOG024 | HTLTENTREM | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100246 | LTE15MHZ0246 | 15YOG032 | KLITREN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100247 | LTE15MHZ0247 | 15YOG034 | BAUSASRAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100248 | LTE15MHZ0248 | 15YOG035 | BABARAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100249 | LTE15MHZ0249 | 15YOG036 | MIROTAKAMPUSXX | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100250 | LTE15MHZ0250 | 15YOG043 | KYAIMOJO | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100251 | LTE15MHZ0251 | 15YOG056 | TAMANSISWA | Activation LTE 15 Mhz + Modernization RF Modul | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100252 | LTE15MHZ0252 | 15YOG068 | APART_SEJAHTERA | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100253 | LTE15MHZ0253 | 15YOG069 | UIN_SELATAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100254 | LTE15MHZ0254 | 15YOG074 | SIDIKAN | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100255 | LTE15MHZ0255 | 15YOG078 | DUSUN_BAWUK | Activation LTE 15 Mhz | Active | CJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100256 | LTE15MHZ0256 | 16PTK003 | IL_RUKO_WPALMA | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100257 | LTE15MHZ0257 | 16PTK007 | IL_WAHID_HASIM_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100258 | LTE15MHZ0258 | 16PTK008 | IL_TNJNG_PURA | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100259 | LTE15MHZ0259 | 16PTK009 | L_KOTABARU_O_XYX | Activation LTE 15 Mhz + Modernization RF Modul | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100260 | LTE15MHZ0260 | 16PTK020 | L_PURNAMA_PTK_O_XYX | Activation LTE 15 Mhz + Modernization RF Modul | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100261 | LTE15MHZ0261 | 16PTK025 | IL_SUWIGNYO | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100262 | LTE15MHZ0262 | 16PTK028 | L_AMPERA_PTK_O_XYX | Activation LTE 15 Mhz + Modernization RF Modul | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100263 | LTE15MHZ0263 | 16PTK033 | IL_ALPOKT_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100264 | LTE15MHZ0264 | 16PTK034 | IL_BRINGN_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100265 | LTE15MHZ0265 | 16PTK035 | IL_MDINTA_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100266 | LTE15MHZ0266 | 16PTK041 | IL_TANJUNG_HILIR | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100267 | LTE15MHZ0267 | 16PTK044 | IL_SIANTAN_HILIR | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100268 | LTE15MHZ0268 | 16PTK047 | SUI_RENGAS_PL | upgrade TRX (EGSM) + Replace Filter | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100269 | LTE15MHZ0269 | 16PTK047 | SUI_RENGAS_PL | Retune Filter Only | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100270 | LTE15MHZ0270 | 16PTK048 | BANJARBARU_PTK_PL | upgrade TRX (EGSM) + Replace Filter | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100271 | LTE15MHZ0271 | 16PTK048 | BANJARBARU_PTK_PL | Retune Filter Only | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100272 | LTE15MHZ0272 | 16PTK066 | IL_TELUK_MULUS | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100273 | LTE15MHZ0273 | 16PTK070 | IL_AYANI_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100274 | LTE15MHZ0274 | 16PTK077 | IL_KAMPUNG_DALAM_PTK_TB | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100275 | LTE15MHZ0275 | 16PTK079 | IL_GOLF_PTK | Activation LTE 15 Mhz | Active | KAL | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100276 | LTE15MHZ0276 | 20COW040 | MLABUHAN | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100277 | LTE15MHZ0277 | 20GSK009 | KEBOMAS | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100278 | LTE15MHZ0278 | 20GSK011 | KOTABARU | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100279 | LTE15MHZ0279 | 20GSK013 | MAYJENSUNGKONO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100280 | LTE15MHZ0280 | 20GSK014 | PERUMDRIYOREJO | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100281 | LTE15MHZ0281 | 20GSK021 | GRESIKKOTA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100282 | LTE15MHZ0282 | 20GSK025 | MANYARKOTA | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100283 | LTE15MHZ0283 | 20GSK034 | SEMENGRESIKOFFICE | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100284 | LTE15MHZ0284 | 20GSK043 | SUCI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100285 | LTE15MHZ0285 | 20GSK047 | JARANGKUWUN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100286 | LTE15MHZ0286 | 20GSK049 | KARANGPILANG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100287 | LTE15MHZ0287 | 20GSK066 | LABUHANGSK | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100288 | LTE15MHZ0288 | 20GSK073 | INDROGRESIK | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100289 | LTE15MHZ0289 | 20SBY001 | SIDOTOPO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100290 | LTE15MHZ0290 | 20SBY007 | ITATS | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100291 | LTE15MHZ0291 | 20SBY008 | TANJUNGPERAK | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100292 | LTE15MHZ0292 | 20SBY009 | YOSINDO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100293 | LTE15MHZ0293 | 20SBY010 | TANDES | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100294 | LTE15MHZ0294 | 20SBY011 | DUKUHKUPANG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100295 | LTE15MHZ0295 | 20SBY014 | MENGANTI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100296 | LTE15MHZ0296 | 20SBY019 | TVRI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100297 | LTE15MHZ0297 | 20SBY022 | KETINTANG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100298 | LTE15MHZ0298 | 20SBY023 | NGINDEN | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100299 | LTE15MHZ0299 | 20SBY024 | PUCANG | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100300 | LTE15MHZ0300 | 20SBY025 | MARGOREJOSBY | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100301 | LTE15MHZ0301 | 20SBY026 | MANUKAN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100302 | LTE15MHZ0302 | 20SBY029 | PETEMON | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100303 | LTE15MHZ0303 | 20SBY036 | TAMBAKSARI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100304 | LTE15MHZ0304 | 20SBY037 | PERAK | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100305 | LTE15MHZ0305 | 20SBY040 | PTNEWCON | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100306 | LTE15MHZ0306 | 20SBY041 | RUNGKUT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100307 | LTE15MHZ0307 | 20SBY042 | DUPAK | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100308 | LTE15MHZ0308 | 20SBY044 | BANYUURIPSBY | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100309 | LTE15MHZ0309 | 20SBY046 | KUSUMABANGSA | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100310 | LTE15MHZ0310 | 20SBY050 | KODAM | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100311 | LTE15MHZ0311 | 20SBY055 | WTCBUILDING | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100312 | LTE15MHZ0312 | 20SBY063 | KEDUNGDORO | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100313 | LTE15MHZ0313 | 20SBY065 | WIYUNG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100314 | LTE15MHZ0314 | 20SBY067 | _PLAZAMARINA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100315 | LTE15MHZ0315 | 20SBY069 | WONOREJO | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100316 | LTE15MHZ0316 | 20SBY073 | RAYATANDES | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100317 | LTE15MHZ0317 | 20SBY074 | KUTISARI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100318 | LTE15MHZ0318 | 20SBY075 | PLOSO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100319 | LTE15MHZ0319 | 20SBY076 | BENDULMERISI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100320 | LTE15MHZ0320 | 20SBY077 | MEDOKANAYU | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100321 | LTE15MHZ0321 | 20SBY078 | KEPUTIH | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100322 | LTE15MHZ0322 | 20SBY080 | LIDAH | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100323 | LTE15MHZ0323 | 20SBY081 | TIDARSBY | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100324 | LTE15MHZ0324 | 20SBY083 | WONOKUSUMO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100325 | LTE15MHZ0325 | 20SBY085 | KERTAJAYA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100326 | LTE15MHZ0326 | 20SBY086 | NGAGEL | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100327 | LTE15MHZ0327 | 20SBY087 | KALIBUTUH | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100328 | LTE15MHZ0328 | 20SBY088 | MASTRIP | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100329 | LTE15MHZ0329 | 20SBY089 | ASEMROWO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100330 | LTE15MHZ0330 | 20SBY090 | JLKENJERAN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100331 | LTE15MHZ0331 | 20SBY092 | PETEMONBARAT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100332 | LTE15MHZ0332 | 20SBY093 | RUNGKUTINDUST | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100333 | LTE15MHZ0333 | 20SBY096 | TENGGILISINDA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100334 | LTE15MHZ0334 | 20SBY097 | TERATAI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100335 | LTE15MHZ0335 | 20SBY105 | BENOWO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100336 | LTE15MHZ0336 | 20SBY106 | DARMOTRDCTR | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100337 | LTE15MHZ0337 | 20SBY107 | BANJARSUGIHAN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100338 | LTE15MHZ0338 | 20SBY109 | PUTAT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100339 | LTE15MHZ0339 | 20SBY111 | MANYARTIRTYS | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100340 | LTE15MHZ0340 | 20SBY112 | DARMOSUKOIM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100341 | LTE15MHZ0341 | 20SBY113 | PETRAIM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100342 | LTE15MHZ0342 | 20SBY115 | MENANGGAL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100343 | LTE15MHZ0343 | 20SBY117 | DIPONEGOROIM3 | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100344 | LTE15MHZ0344 | 20SBY118 | GAJAHMADAIM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100345 | LTE15MHZ0345 | 20SBY121 | MANYARKERT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100346 | LTE15MHZ0346 | 20SBY124 | _ROYALPLAZA | Activation LTE 15 Mhz + Upgrade RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100347 | LTE15MHZ0347 | 20SBY128 | DHARMAWANGSA | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100348 | LTE15MHZ0348 | 20SBY129 | DARMAHUSADA | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100349 | LTE15MHZ0349 | 20SBY141 | PAKIS_PL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100350 | LTE15MHZ0350 | 20SBY144 | LIDAHWETAN_RT | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100351 | LTE15MHZ0351 | 20SBY183 | KETINTANGIM3 | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100352 | LTE15MHZ0352 | 20SBY197 | KEDUNGDOROIM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100353 | LTE15MHZ0353 | 20SBY200 | JAGIR_IM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100354 | LTE15MHZ0354 | 20SBY201 | MANYAR_IM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100355 | LTE15MHZ0355 | 20SBY206 | KEDUNGCOWK | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100356 | LTE15MHZ0356 | 20SBY209 | KEDURUS | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100357 | LTE15MHZ0357 | 20SBY211 | WISMAMUKTI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100358 | LTE15MHZ0358 | 20SBY214 | JARAK | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100359 | LTE15MHZ0359 | 20SBY215 | MARGOMLSBY | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100360 | LTE15MHZ0360 | 20SBY218 | GALAXI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100361 | LTE15MHZ0361 | 20SBY219 | BRATANG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100362 | LTE15MHZ0362 | 20SBY220 | JETISSBY | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100363 | LTE15MHZ0363 | 20SBY223 | RUNGKUTASRI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100364 | LTE15MHZ0364 | 20SBY225 | KEBRAON | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100365 | LTE15MHZ0365 | 20SBY226 | JEMURSARI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100366 | LTE15MHZ0366 | 20SBY244 | SEPANJANG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100367 | LTE15MHZ0367 | 20SBY245 | MDURYAT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100368 | LTE15MHZ0368 | 20SBY254 | SEPANJANGIM3 | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100369 | LTE15MHZ0369 | 20SBY272 | GUNUNGSARISBY | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100370 | LTE15MHZ0370 | 20SBY287 | BASUKIRAHMAT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100371 | LTE15MHZ0371 | 20SBY301 | TECGBL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100372 | LTE15MHZ0372 | 20SBY305 | JEMURWONOSARI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100373 | LTE15MHZ0373 | 20SBY308 | MULYOREJO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100374 | LTE15MHZ0374 | 20SBY312 | BULAKTBG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100375 | LTE15MHZ0375 | 20SBY313 | TANAHKALIKEDINDING | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100376 | LTE15MHZ0376 | 20SBY317 | PERAKUTARA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100377 | LTE15MHZ0377 | 20SBY320 | RUNGKUTKIDUL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100378 | LTE15MHZ0378 | 20SBY324 | SIDOTOPOSBYPL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100379 | LTE15MHZ0379 | 20SBY327 | SUMURWELUTTBG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100380 | LTE15MHZ0380 | 20SBY328 | DRSOETOMOTBG | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100381 | LTE15MHZ0381 | 20SBY334 | ITS_TB | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100382 | LTE15MHZ0382 | 20SBY338 | POLDA_SBY | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100383 | LTE15MHZ0383 | 20SBY345 | BRATANGPL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100384 | LTE15MHZ0384 | 20SBY354 | SHAM_FM | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100385 | LTE15MHZ0385 | 20SDA003 | TOLLSIDOARJO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100386 | LTE15MHZ0386 | 20SDA006 | ALOHA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100387 | LTE15MHZ0387 | 20SDA008 | CANDI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100388 | LTE15MHZ0388 | 20SDA013 | TANGGULANGIN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100389 | LTE15MHZ0389 | 20SDA014 | CITRAFAJAR | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100390 | LTE15MHZ0390 | 20SDA015 | DELTASARI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100391 | LTE15MHZ0391 | 20SDA016 | ISPATINDO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100392 | LTE15MHZ0392 | 20SDA019 | JENGGOLO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100393 | LTE15MHZ0393 | 20SDA020 | SELATANSURABA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100394 | LTE15MHZ0394 | 20SDA021 | SUKODONO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100395 | LTE15MHZ0395 | 20SDA022 | WONOAYU | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100396 | LTE15MHZ0396 | 20SDA024 | KRIANCITY | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100397 | LTE15MHZ0397 | 20SDA025 | LEBO | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100398 | LTE15MHZ0398 | 20SDA026 | GEDANGANCITY | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100399 | LTE15MHZ0399 | 20SDA027 | WAGEPERMAI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100400 | LTE15MHZ0400 | 20SDA033 | TAMANPUSPA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100401 | LTE15MHZ0401 | 20SDA038 | AHMADYANIIM3 | Activation LTE 15 Mhz + Modernization RF Modul | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100402 | LTE15MHZ0402 | 20SDA039 | GELAM | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100403 | LTE15MHZ0403 | 20SDA057 | SIDOARJOKT | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100404 | LTE15MHZ0404 | 20SDA058 | SIDOKAREPL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100405 | LTE15MHZ0405 | 20SDA059 | KEMIRI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100406 | LTE15MHZ0406 | 20SDA060 | SENDENGMJN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100407 | LTE15MHZ0407 | 20SDA063 | WADUNGASRI | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100408 | LTE15MHZ0408 | 20SDA064 | TROPODO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100409 | LTE15MHZ0409 | 20SDA065 | TAMANALOHA | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100410 | LTE15MHZ0410 | 20SDA068 | JUMPUTREJO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100411 | LTE15MHZ0411 | 20SDA069 | WONOAYUKRIAN | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100412 | LTE15MHZ0412 | 20SDA111 | SAWOTRATAP | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100413 | LTE15MHZ0413 | 20SDA115 | JLBRIGJENKATAMSO | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100414 | LTE15MHZ0414 | 20SDA116 | TAMBAKSAWAHPL | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100415 | LTE15MHZ0415 | 20SDA129 | GEDANGANTB | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100416 | LTE15MHZ0416 | 20SDA130 | BEBEKANTB | Activation LTE 15 Mhz | Active | EJ | LTE 15 MHz | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100417 | LTEMU33S0417 | 14DMK031 | DEMAKTIMUR | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100418 | LTEMU33S0418 | 14KLT019 | WNSR_KLTSM | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100419 | LTEMU33S0419 | 14KND034 | WELERIBARAT | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100420 | LTEMU33S0420 | 14KND035 | SIDOMUKTI | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100421 | LTEMU33S0421 | 14KND040 | SUMBERSARI_KDL | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100422 | LTEMU33S0422 | 14KND041 | TEGOREJO_KDL | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100423 | LTEMU33S0423 | 14SMG078 | U_TUGUKP | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100424 | LTEMU33S0424 | 14SMG088 | WONOLOPOPL | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100425 | LTEMU33S0425 | 14SMG110 | U_POLAMAN | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100426 | LTEMU33S0426 | 14SMG125 | KERTOSARI | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100427 | LTEMU33S0427 | 14SMG200 | PEDURUNGANLORPL | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100428 | LTEMU33S0428 | 14SMG206 | AMPOSARIPL | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100429 | LTEMU33S0429 | 14UNR033 | PRINGAPUSUTARA | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100430 | LTEMU33S0430 | 14UNR067 | LEREP_IT | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100431 | LTEMU33S0431 | 15BTL058 | SELOPAMIORO_IT | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100432 | LTEMU33S0432 | 15BTL069 | BUGISANMT | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100433 | LTEMU33S0433 | 15WAT021 | PANJATANSM | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100434 | LTEMU33S0434 | 15WOS005 | PLAYEN | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100435 | LTEMU33S0435 | 15WOS033 | Pakaryan | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100436 | LTEMU33S0436 | 15YOG060 | GEDUNGKIWO | New LTE 1800 | Active | CJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100437 | LTEMU33S0437 | 20GSK040 | SUCI MANYAR | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100438 | LTEMU33S0438 | 20GSK081 | SUNAN GIRI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100439 | LTEMU33S0439 | 20GSK083 | U_USMAN_SADAR | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100440 | LTEMU33S0440 | 20SBY298 | MICMULYOSARI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100441 | LTEMU33S0441 | 20SBY302 | RSHAJI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100442 | LTEMU33S0442 | 20SBY306 | L_KARAHXL | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100443 | LTEMU33S0443 | 20SDA044 | SIMPANG | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100444 | LTEMU33S0444 | 20SDA050 | KARANGPURI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100445 | LTEMU33S0445 | 20SDA052 | WADUNG_SARI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100446 | LTEMU33S0446 | 20SDA053 | BYPASS_JUANDA | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100447 | LTEMU33S0447 | 20SDA055 | U_DUKUH_SARI | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100448 | LTEMU33S0448 | 20SDA096 | U_PLOSOKREMBT | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1
100449 | LTEMU33S0449 | 20SDA141 | SUKOSBYMN | New LTE 1800 | Active | EJ | LTE Mini Umbrella 33 Site | BTS | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  |  |  | FALSE | [6 empty] | 1